## Read me
Mail OPS content map: what has to be written and built
Maps every topic of the 15-day curriculum to its LMS item, Quip articles and Training Kit items. Counts below are formulas over the other sheets and update as you change statuses.
Quip articles by type and week first needed
Article type | Week 1 | Week 2 | Week 3
Hub | 7 | 0 | 0
Concept | 9 | 5 | 0
Workflow / SOP | 6 | 6 | 3
Tool Guide | 10 | 0 | 0
Decision Guide | 1 | 3 | 1
Reference | 4 | 1 | 1
Change Log | 2 | 0 | 0
Total | 39 | 15 | 5
Writing progress
Status | Quip articles | LMS items | Training Kit
Not started | 59 | 29 | 55
Drafting | 0 | 0 | 0
Storyboarding | 0 | 0 | 0
In review | 0 | 0 | 0
Approved | 0 | 0 | 0
Built | 0 | 0 | 0
Published | 0 | 0 | 0
Total | 59 | 29 | 55
LMS and Training Kit items by type
Item type | Count
Module | 22
Check-only module | 4
Assessment | 3
Total | 29
Trainer Guide | 39
Hands-on Activity | 16
Total | 55
How to use this workbook
Curriculum map | Start here to see what each curriculum row becomes. Edit only if the curriculum changes.
Quip articles | The writing backlog, in the order articles are first needed. Fill in the yellow columns: legacy triage result, legacy link, owner, writer, status.
LMS items | Every module, check-only module and assessment, with the articles it links to. Adjust planned questions and status in the yellow columns.
Training Kit | Trainer Guides and Hands-on Activities for the restricted folder. Fill in owner and status.
Yellow cells | Inputs for you to fill in. Everything else is the plan, or a formula.
Decisions, gaps and assumptions
Scope | Every topic row of the 15-day curriculum is mapped. Daily recaps and wrap-ups are not listed row by row; one Trainer Guide (TG-GEN-recap-wrap) covers how to run them.
LMS modules | SPL and Blended rows each become one LMS module (M-Wn-nn), numbered in curriculum order within each week.
Decision to confirm | SME-led ILT sessions that carry core process content (URL/SUPs, outbound abuse types, account actions, campaigns) get a check-only LMS module: reading tasks plus a comprehension check, no teaching blocks. The guidelines pack says ILT rows are attendance only; this is a proposed exception so these topics are not tested for the first time on Day 10.
Decision to confirm | Cross-area casework articles (end-to-end case handling, root cause codes, Radar hand-off, escalation contacts) are filed in 00 Start Here with GEN IDs, because they apply to inbound, outbound and Postmaster alike.
Gap | The Day 15 practical includes an inbound triage case, but no curriculum session teaches inbound triage beyond 'Actioning a case' (KA-GEN-005). SME to confirm whether KA-GEN-005 is enough or an inbound triage Workflow (KA-IN-003) is needed.
Gap | URL/SUP (KA-IN-001) is still undefined in the source material. Its type, scope and timing depend on the SME.
ID change | The worked examples in the guidelines pack and the two example docs call the Heimdall module M-W1-07. In curriculum order it is M-W1-06. Update the examples if you keep this numbering.
Legacy | Every article starts as 'To triage'. During legacy triage, set it to New, Keep, or Merge from legacy, and record the legacy link.
Assessments | A-D06 (Week 1 knowledge check), A-D10 (Week 2 practical) and A-D15 (final certification) draw questions from the articles tested that week. Their question counts are set in the LMS items sheet.
Source | Source material refers to the Module 1 learning guide sections used in the curriculum, and to the SME inputs list in the curriculum workbook.

## Curriculum map
Content map: 15-day curriculum to LMS, Quip and Training Kit
One row per curriculum topic. Daily recaps and wrap-ups are run from TG-GEN-recap-wrap and are not listed. IDs follow the guidelines pack; see Read me for decisions to confirm.
Day | Week | Curriculum topic | Modality | Mins | LMS item | LMS item type | Quip articles | Trainer Guide | Hands-on Activity | Content readiness
1 | 1 | Team Mission & Objectives - Mail OPS | SPL | 75 | M-W1-01 | Module | KA-FND-001 |  |  | Partly ready – SME to add
1 | 1 | Privacy principles and data handling boundaries | SPL | 45 | M-W1-02 | Module | KA-FND-002 |  |  | Partly ready – SME to add
1 | 1 | iCloud and iCloud Mail | SPL | 75 | M-W1-03 | Module | KA-FND-003 |  |  | Ready – Module 1 guide
1 | 1 | iCloud+ mail features | SPL | 60 | M-W1-04 | Module | KA-FND-004 |  |  | Ready – Module 1 guide
1 | 1 | Hands on: iCloud and iCloud+ Mail | Activity | 120 | None | Attendance only | KA-FND-003, KA-FND-004 | TG-D01-icloud-handson | HA-FND-001 | Ops to arrange
2 | 1 | Mail flow architecture | Blended | 90 | M-W1-05 | Module | KA-FND-005 | TG-M-W1-05 |  | Ready – Module 1 guide
2 | 1 | Tool Overview: Heimdall | SPL | 60 | M-W1-06 | Module | KA-TOOL-002, KA-FND-006, KA-OUT-020, KA-OUT-021 |  |  | Partly ready – SME to add
2 | 1 | Tool Walkthrough: Heimdall | ILT | 60 | None | Attendance only | KA-TOOL-002, KA-OUT-020, KA-OUT-022 | TG-D02-heimdall-walkthrough | HA-TOOL-002 | SME to provide
2 | 1 | URL/SUPs | ILT | 60 | M-W1-07 | Check-only module | KA-IN-001 | TG-D02-url-sups |  | SME to provide
2 | 1 | Hands on: URL/SUPs | Activity | 60 | None | Attendance only | KA-IN-001 | TG-D02-url-sups | HA-IN-001 | SME to provide
3 | 1 | Tools overview - part 1 (Splunk) - Investigate | Blended | 90 | M-W1-08 | Module | KA-TOOL-003, KA-TOOL-004 | TG-M-W1-08 |  | SME to provide
3 | 1 | Hands on: Splunk | Activity | 30 | None | Attendance only | KA-TOOL-004 | TG-M-W1-08 | HA-TOOL-001 | SME to provide
3 | 1 | Tools overview - part 1 (Sonar) - Investigate | SPL | 60 | M-W1-09 | Module | KA-TOOL-005, KA-GEN-006 |  |  | Partly ready – SME to add
3 | 1 | Hands on: Sonar | Activity | 60 | None | Attendance only | KA-TOOL-005, KA-GEN-006 | TG-D03-sonar-handson | HA-TOOL-003 | Ops to arrange
3 | 1 | Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | Blended | 90 | M-W1-10 | Module | KA-TOOL-006, KA-TOOL-007, KA-TOOL-008 | TG-M-W1-10 |  | Partly ready – SME to add
4 | 1 | Tools overview - part 3 (Radar, Slack, Quip) - Engineer | SPL | 45 | M-W1-11 | Module | KA-TOOL-009, KA-TOOL-010 |  |  | Partly ready – SME to add
4 | 1 | Tools overview - part 4 (Khiron, iHawk) - Other tools | SPL | 45 | M-W1-12 | Module | KA-TOOL-011, KA-TOOL-012 |  |  | SME to provide
4 | 1 | Hands on: Tools by stage | Activity | 60 | None | Attendance only | KA-TOOL-001 | TG-D04-tools-by-stage | HA-TOOL-004 | Trainer to build
4 | 1 | The 14-stage milter chain | Blended | 90 | M-W1-13 | Module | KA-FND-007 | TG-M-W1-13 |  | Ready – Module 1 guide
4 | 1 | Hands on: Header analysis with samples | Activity | 90 | None | Attendance only | KA-FND-008, KA-FND-007 | TG-D04-header-analysis | HA-FND-002 | SME to provide
5 | 1 | Inbound Mail Flow: Deep Dive | Blended | 90 | M-W1-14 | Module | KA-FND-009 | TG-M-W1-14 |  | Ready – Module 1 guide
5 | 1 | Hands on: Inbound mail tracing | Activity | 75 | None | Attendance only | KA-IN-002 | TG-D05-inbound-tracing | HA-IN-002 | SME to provide
5 | 1 | Outbound Mail Flow: Deep Dive | Blended | 90 | M-W1-15 | Module | KA-FND-010 | TG-M-W1-15 |  | Ready – Module 1 guide
5 | 1 | Hands on: Outbound mail tracing | Activity | 75 | None | Attendance only | KA-OUT-001 | TG-D05-outbound-tracing | HA-OUT-001 | SME to provide
6 | 2 | Week 1 Knowledge Check | Assessment | 60 | A-D06 | Assessment |  | TG-D06-knowledge-check |  | Trainer to build
6 | 2 | Knowledge Check Review | Activity | 45 | None | Attendance only |  | TG-D06-knowledge-check |  | Trainer to build
6 | 2 | Our operating model: Identify, Mitigate, Engineer | Blended | 90 | M-W2-01 | Module | KA-FND-011 | TG-M-W2-01 |  | Ready – Module 1 guide
6 | 2 | Abuse landscape | SPL | 60 | M-W2-02 | Module | KA-FND-012 |  |  | Ready – Module 1 guide
6 | 2 | Abuse landscape in iCloud Outbound | ILT | 120 | M-W2-03 | Check-only module | KA-OUT-002, KA-OUT-003 | TG-D06-outbound-abuse |  | SME to provide
7 | 2 | Types/Actions on accounts | ILT | 90 | M-W2-04 | Check-only module | KA-OUT-010, KA-OUT-011 | TG-D07-account-actions |  | SME to provide
7 | 2 | Actioning a case | Blended | 90 | M-W2-05 | Module | KA-GEN-005, KA-GEN-006, KA-FND-013 | TG-M-W2-05 |  | Partly ready – SME to add
7 | 2 | Hands-on with sample accounts | Activity | 150 | None | Attendance only | KA-OUT-010, KA-OUT-011, KA-OUT-012 | TG-D07-sample-accounts | HA-OUT-002 | SME to provide
8 | 2 | Hands-on with sample accounts | Activity | 270 | None | Attendance only | KA-OUT-010, KA-OUT-011, KA-OUT-012 | TG-D08-sample-accounts | HA-OUT-003 | SME to provide
8 | 2 | Trainer case review | ILT | 60 | None | Attendance only |  | TG-D08-case-review |  | Trainer to build
9 | 2 | Working with Postmaster | Blended | 90 | M-W2-06 | Module | KA-PM-001, KA-PM-002, KA-PM-003, KA-PM-004 | TG-M-W2-06 |  | Partly ready – SME to add
9 | 2 | Hands on: Postmaster cases | Activity | 90 | None | Attendance only | KA-PM-002, KA-PM-003, KA-PM-004 | TG-D09-postmaster-handson | HA-PM-001 | SME to provide
9 | 2 | Other Ops workflow - Spike in user spam reports | Blended | 60 | M-W2-07 | Module | KA-PB-001 | TG-M-W2-07 |  | Ready – Module 1 guide
9 | 2 | Other Ops workflow - Outbound abuse | Blended | 90 | M-W2-08 | Module | KA-PB-002 | TG-M-W2-08 |  | Ready – Module 1 guide
10 | 2 | Hands on: Postmaster and triage scenarios | Activity | 120 | None | Attendance only | KA-PM-002, KA-PB-001, KA-PB-002 | TG-D10-scenarios | HA-PB-001 | Trainer to build
10 | 2 | Week 2 Practical Assessment | Assessment | 120 | A-D10 | Assessment |  | TG-D10-assessment |  | Trainer to build
10 | 2 | Assessment Debrief | ILT | 90 | None | Attendance only |  | TG-D10-assessment |  | Trainer to build
11 | 3 | Identifying and actioning on campaigns | ILT | 120 | M-W3-01 | Check-only module | KA-OUT-023, KA-OUT-024, KA-OUT-020, KA-OUT-021 | TG-D11-campaigns |  | SME to provide
11 | 3 | Hands on: Campaigns | Activity | 165 | None | Attendance only | KA-OUT-023, KA-OUT-024, KA-TOOL-004 | TG-D11-campaigns | HA-OUT-004 | SME to provide
11 | 3 | Engineering hand-off: writing a Radar | SPL | 45 | M-W3-02 | Module | KA-GEN-007, KA-TOOL-009 |  |  | Ready – Module 1 guide
12 | 3 | Outbound Hands-on | Activity | 270 | None | Attendance only | KA-OUT-003, KA-OUT-010, KA-OUT-011, KA-PB-002 | TG-D12-outbound-handson | HA-OUT-005 | SME to provide
12 | 3 | Trainer case review | ILT | 60 | None | Attendance only |  | TG-D12-case-review |  | Trainer to build
13 | 3 | Outbound Hands-on | Activity | 180 | None | Attendance only | KA-OUT-003, KA-OUT-010, KA-OUT-023 | TG-D13-outbound-handson | HA-OUT-006 | SME to provide
13 | 3 | Shadow a proactive hunt | Activity | 90 | None | Attendance only | KA-PB-003 | TG-D13-shadowing |  | Ops to arrange
13 | 3 | Proofpoint and Heimdall rule review | ILT | 60 | None | Attendance only | KA-TOOL-002, KA-TOOL-006, KA-OUT-021 | TG-D13-rule-review |  | Ops to arrange
14 | 3 | Nesting: supervised mixed queue | Activity | 240 | None | Attendance only | KA-GEN-005 | TG-D14-nesting |  | Ops to arrange
14 | 3 | QA feedback session | ILT | 60 | None | Attendance only |  | TG-D14-nesting |  | Ops to arrange
14 | 3 | Guardrails and escalation refresher | SPL | 30 | M-W3-03 | Module | KA-FND-013, KA-GEN-008 |  |  | Ready – Module 1 guide
15 | 3 | Final Certification - Theory | Assessment | 60 | A-D15 | Assessment |  | TG-D15-certification |  | Trainer to build
15 | 3 | Final Certification - Practical | Assessment | 150 | A-D15 | Assessment |  | TG-D15-certification |  | Trainer to build
15 | 3 | Results and development plans | ILT | 60 | None | Attendance only |  | TG-D15-results |  | Trainer to build
15 | 3 | Transition to process | ILT | 60 | None | Attendance only | KA-GEN-001 | TG-D15-transition |  | Ops to arrange
15 | 3 | Programme close and feedback | Activity | 45 | None | Attendance only |  | TG-D15-results |  | Trainer to build

## Quip articles
Quip article inventory and writing backlog
Sorted by the day each article is first needed, so it doubles as the writing order. Yellow columns are yours to fill in.
KA ID | Title | Type | Folder | First needed (day) | Week | Used in (curriculum rows) | Times used | Linked LMS items | Source material | New or legacy | Legacy link | Owner (SME / Ops) | Writer | Status
KA-FND-000 | Foundations hub | Hub | 01 Foundations | 1 | 1 | Before launch (navigation and setup) | 0 | None | Trainer to build | To triage |  |  |  | Not started
KA-FND-001 | Mail OPS mission, team and roles | Concept | 01 Foundations | 1 | 1 | D1: Team Mission & Objectives - Mail OPS | 1 | M-W1-01, A-D06, A-D15 | Guide §1 + SME (Apple ecosystem, T&S intro) | To triage |  |  |  | Not started
KA-FND-002 | Privacy principles and data handling | Concept | 01 Foundations | 1 | 1 | D1: Privacy principles and data handling boundaries | 1 | M-W1-02, A-D06, A-D15 | Guide §1, §15 + SME (GDPR, incidents) | To triage |  |  |  | Not started
KA-FND-003 | Apple Account, iCloud and iCloud Mail | Concept | 01 Foundations | 1 | 1 | D1: iCloud and iCloud Mail D1: Hands on: iCloud and iCloud+ Mail | 2 | M-W1-03, A-D06, A-D15 | Guide §2, §3, §11 | To triage |  |  |  | Not started
KA-FND-004 | iCloud+ mail features | Concept | 01 Foundations | 1 | 1 | D1: iCloud+ mail features D1: Hands on: iCloud and iCloud+ Mail | 2 | M-W1-04, A-D06, A-D15 | Guide §2, §8 | To triage |  |  |  | Not started
KA-GEN-001 | Mail OPS home hub | Hub | 00 Start Here | 1 | 1 | D15: Transition to process | 1 | None | Trainer to build | To triage |  |  |  | Not started
KA-GEN-002 | Mail OPS Glossary | Reference | 00 Start Here | 1 | 1 | Before launch (navigation and setup) | 0 | None | Module 1 guide §14 Ops terms | To triage |  |  |  | Not started
KA-GEN-003 | What's New | Change Log | 00 Start Here | 1 | 1 | Before launch (navigation and setup) | 0 | None | Set up once | To triage |  |  |  | Not started
KA-GEN-004 | What's New Archive | Change Log | 99 Archive | 1 | 1 | Before launch (navigation and setup) | 0 | None | Set up once | To triage |  |  |  | Not started
KA-IN-000 | Inbound hub | Hub | 03 Inbound | 1 | 1 | Before launch (navigation and setup) | 0 | None | Trainer to build | To triage |  |  |  | Not started
KA-OUT-000 | Outbound hub | Hub | 04 Outbound | 1 | 1 | Before launch (navigation and setup) | 0 | None | Trainer to build | To triage |  |  |  | Not started
KA-PB-000 | Playbooks hub | Hub | 06 Playbooks | 1 | 1 | Before launch (navigation and setup) | 0 | None | Trainer to build | To triage |  |  |  | Not started
KA-PM-000 | Postmaster hub | Hub | 05 Postmaster | 1 | 1 | Before launch (navigation and setup) | 0 | None | Trainer to build | To triage |  |  |  | Not started
KA-TOOL-000 | Tools hub | Hub | 02 Tools | 1 | 1 | Before launch (navigation and setup) | 0 | None | Trainer to build | To triage |  |  |  | Not started
KA-FND-005 | Mail flow architecture and email headers | Concept | 01 Foundations | 2 | 1 | D2: Mail flow architecture | 1 | M-W1-05, A-D06, A-D15 | Guide §4, §5, §7, §14 | To triage |  |  |  | Not started
KA-FND-006 | How mail classification works | Concept | 01 Foundations | 2 | 1 | D2: Tool Overview: Heimdall | 1 | M-W1-06, A-D06, A-D15 | Guide §6 + SME | To triage |  |  |  | Not started
KA-IN-001 | Handle a URL/SUP request | Workflow / SOP | 03 Inbound | 2 | 1 | D2: URL/SUPs D2: Hands on: URL/SUPs | 2 | M-W1-07, A-D06, A-D15 | SME (scope to be confirmed) | To triage |  |  |  | Not started
KA-OUT-020 | Allowlist or blocklist a campaign | Workflow / SOP | 04 Outbound | 2 | 1 | D2: Tool Overview: Heimdall D2: Tool Walkthrough: Heimdall D11: Identifying and actioning on campaigns | 3 | M-W1-06, M-W3-01, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-OUT-021 | Choosing between allowlist and blocklist | Decision Guide | 04 Outbound | 2 | 1 | D2: Tool Overview: Heimdall D11: Identifying and actioning on campaigns D13: Proofpoint and Heimdall rule review | 3 | M-W1-06, M-W3-01, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-OUT-022 | Edit an existing rule | Workflow / SOP | 04 Outbound | 2 | 1 | D2: Tool Walkthrough: Heimdall | 1 | A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-TOOL-002 | Heimdall Tool Guide | Tool Guide | 02 Tools | 2 | 1 | D2: Tool Overview: Heimdall D2: Tool Walkthrough: Heimdall D13: Proofpoint and Heimdall rule review | 3 | M-W1-06, A-D06, A-D15 | Guide §6 + SME (UI, naming, rules) | To triage |  |  |  | Not started
KA-GEN-006 | Root cause and sub root cause codes | Reference | 00 Start Here | 3 | 1 | D3: Tools overview - part 1 (Sonar) - Investigate D3: Hands on: Sonar D7: Actioning a case | 3 | M-W1-09, M-W2-05, A-D06, A-D10, A-D15 | Guide §14 + SME | To triage |  |  |  | Not started
KA-TOOL-003 | Splunk Tool Guide | Tool Guide | 02 Tools | 3 | 1 | D3: Tools overview - part 1 (Splunk) - Investigate | 1 | M-W1-08, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-TOOL-004 | Splunk indexes and query library | Reference | 02 Tools | 3 | 1 | D3: Tools overview - part 1 (Splunk) - Investigate D3: Hands on: Splunk D11: Hands on: Campaigns | 3 | M-W1-08, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-TOOL-005 | Sonar Tool Guide | Tool Guide | 02 Tools | 3 | 1 | D3: Tools overview - part 1 (Sonar) - Investigate D3: Hands on: Sonar | 2 | M-W1-09, A-D06, A-D15 | Guide §10, §14 + SME | To triage |  |  |  | Not started
KA-TOOL-006 | Proofpoint (PPS/TAP) Tool Guide | Tool Guide | 02 Tools | 3 | 1 | D3: Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate D13: Proofpoint and Heimdall rule review | 2 | M-W1-10, A-D06, A-D15 | Guide §6, §10 + SME | To triage |  |  |  | Not started
KA-TOOL-007 | Bazooka Tool Guide | Tool Guide | 02 Tools | 3 | 1 | D3: Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | 1 | M-W1-10, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-TOOL-008 | Gattler Tool Guide | Tool Guide | 02 Tools | 3 | 1 | D3: Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | 1 | M-W1-10, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-FND-007 | The 14-stage milter chain | Concept | 01 Foundations | 4 | 1 | D4: The 14-stage milter chain D4: Hands on: Header analysis with samples | 2 | M-W1-13, A-D06, A-D15 | Guide §6 | To triage |  |  |  | Not started
KA-FND-008 | Analyse an email header | Workflow / SOP | 01 Foundations | 4 | 1 | D4: Hands on: Header analysis with samples | 1 | A-D06, A-D15 | Guide §6, §14 + SME header samples | To triage |  |  |  | Not started
KA-TOOL-001 | Tools by stage | Reference | 02 Tools | 4 | 1 | D4: Hands on: Tools by stage | 1 | A-D06, A-D15 | Guide §10 | To triage |  |  |  | Not started
KA-TOOL-009 | Radar Tool Guide | Tool Guide | 02 Tools | 4 | 1 | D4: Tools overview - part 3 (Radar, Slack, Quip) - Engineer D11: Engineering hand-off: writing a Radar | 2 | M-W1-11, M-W3-02, A-D06, A-D15 | Guide §10 | To triage |  |  |  | Not started
KA-TOOL-010 | Slack and Quip in Mail OPS | Tool Guide | 02 Tools | 4 | 1 | D4: Tools overview - part 3 (Radar, Slack, Quip) - Engineer | 1 | M-W1-11, A-D06, A-D15 | Guide §10 | To triage |  |  |  | Not started
KA-TOOL-011 | Khiron Tool Guide | Tool Guide | 02 Tools | 4 | 1 | D4: Tools overview - part 4 (Khiron, iHawk) - Other tools | 1 | M-W1-12, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-TOOL-012 | iHawk Tool Guide | Tool Guide | 02 Tools | 4 | 1 | D4: Tools overview - part 4 (Khiron, iHawk) - Other tools | 1 | M-W1-12, A-D06, A-D15 | SME | To triage |  |  |  | Not started
KA-FND-009 | Inbound mail flow: deep dive | Concept | 01 Foundations | 5 | 1 | D5: Inbound Mail Flow: Deep Dive | 1 | M-W1-14, A-D06, A-D15 | Guide §5, §6 | To triage |  |  |  | Not started
KA-FND-010 | Outbound mail flow: deep dive | Concept | 01 Foundations | 5 | 1 | D5: Outbound Mail Flow: Deep Dive | 1 | M-W1-15, A-D06, A-D15 | Guide §7 | To triage |  |  |  | Not started
KA-IN-002 | Trace an inbound message | Workflow / SOP | 03 Inbound | 5 | 1 | D5: Hands on: Inbound mail tracing | 1 | A-D06, A-D15 | Guide §5, §6 | To triage |  |  |  | Not started
KA-OUT-001 | Trace an outbound message and read bounces | Workflow / SOP | 04 Outbound | 5 | 1 | D5: Hands on: Outbound mail tracing | 1 | A-D06, A-D15 | Guide §7, §14 | To triage |  |  |  | Not started
KA-FND-011 | Operating model: Identify, Mitigate, Engineer | Concept | 01 Foundations | 6 | 2 | D6: Our operating model: Identify, Mitigate, Engineer | 1 | M-W2-01, A-D10, A-D15 | Guide §1, §10 | To triage |  |  |  | Not started
KA-FND-012 | Abuse landscape | Concept | 01 Foundations | 6 | 2 | D6: Abuse landscape | 1 | M-W2-02, A-D10, A-D15 | Guide §9 | To triage |  |  |  | Not started
KA-OUT-002 | Outbound abuse types | Concept | 04 Outbound | 6 | 2 | D6: Abuse landscape in iCloud Outbound | 1 | M-W2-03, A-D10, A-D15 | Guide §8, §9 + SME (bad forward, login alias, Apple ID) | To triage |  |  |  | Not started
KA-OUT-003 | Identifying the outbound abuse type | Decision Guide | 04 Outbound | 6 | 2 | D6: Abuse landscape in iCloud Outbound D12: Outbound Hands-on D13: Outbound Hands-on | 3 | M-W2-03, A-D10, A-D15 | SME | To triage |  |  |  | Not started
KA-FND-013 | Guardrails and non-negotiables | Concept | 01 Foundations | 7 | 2 | D7: Actioning a case D14: Guardrails and escalation refresher | 2 | M-W2-05, M-W3-03, A-D10, A-D15 | Guide §15 | To triage |  |  |  | Not started
KA-GEN-005 | Work a case end to end: triage, mitigate, record | Workflow / SOP | 00 Start Here | 7 | 2 | D7: Actioning a case D14: Nesting: supervised mixed queue | 2 | M-W2-05, A-D10, A-D15 | Guide §10, §14, §15 + SME SOP | To triage |  |  |  | Not started
KA-OUT-010 | Account actions by account type | Decision Guide | 04 Outbound | 7 | 2 | D7: Types/Actions on accounts D7: Hands-on with sample accounts D8: Hands-on with sample accounts D12: Outbound Hands-on D13: Outbound Hands-on | 5 | M-W2-04, A-D10, A-D15 | Guide §13B, §14 + SME | To triage |  |  |  | Not started
KA-OUT-011 | Action an account and record the outcome | Workflow / SOP | 04 Outbound | 7 | 2 | D7: Types/Actions on accounts D7: Hands-on with sample accounts D8: Hands-on with sample accounts D12: Outbound Hands-on | 4 | M-W2-04, A-D10, A-D15 | Guide §13B, §15 + SME | To triage |  |  |  | Not started
KA-OUT-012 | Action a Hide My Email abuse case | Workflow / SOP | 04 Outbound | 7 | 2 | D7: Hands-on with sample accounts D8: Hands-on with sample accounts | 2 | A-D10, A-D15 | Guide §8 + SME | To triage |  |  |  | Not started
KA-PB-001 | Spike in user spam reports | Workflow / SOP | 06 Playbooks | 9 | 2 | D9: Other Ops workflow - Spike in user spam reports D10: Hands on: Postmaster and triage scenarios | 2 | M-W2-07, A-D10, A-D15 | Guide §13A | To triage |  |  |  | Not started
KA-PB-002 | Outbound abuse playbook | Workflow / SOP | 06 Playbooks | 9 | 2 | D9: Other Ops workflow - Outbound abuse D10: Hands on: Postmaster and triage scenarios D12: Outbound Hands-on | 3 | M-W2-08, A-D10, A-D15 | Guide §13B | To triage |  |  |  | Not started
KA-PM-001 | Postmaster policy positions | Concept | 05 Postmaster | 9 | 2 | D9: Working with Postmaster | 1 | M-W2-06, A-D10, A-D15 | Guide §12 | To triage |  |  |  | Not started
KA-PM-002 | Work a Postmaster case | Workflow / SOP | 05 Postmaster | 9 | 2 | D9: Working with Postmaster D9: Hands on: Postmaster cases D10: Hands on: Postmaster and triage scenarios | 3 | M-W2-06, A-D10, A-D15 | Guide §12 | To triage |  |  |  | Not started
KA-PM-003 | Postmaster case types and causes | Decision Guide | 05 Postmaster | 9 | 2 | D9: Working with Postmaster D9: Hands on: Postmaster cases | 2 | M-W2-06, A-D10, A-D15 | Guide §12 | To triage |  |  |  | Not started
KA-PM-004 | Postmaster reply templates | Reference | 05 Postmaster | 9 | 2 | D9: Working with Postmaster D9: Hands on: Postmaster cases | 2 | M-W2-06, A-D10, A-D15 | SME (approved templates) | To triage |  |  |  | Not started
KA-GEN-007 | Write an engineering hand-off (Radar) | Workflow / SOP | 00 Start Here | 11 | 3 | D11: Engineering hand-off: writing a Radar | 1 | M-W3-02, A-D15 | Guide §10 | To triage |  |  |  | Not started
KA-OUT-023 | Identify and cluster a campaign | Workflow / SOP | 04 Outbound | 11 | 3 | D11: Identifying and actioning on campaigns D11: Hands on: Campaigns D13: Outbound Hands-on | 3 | M-W3-01, A-D15 | Guide §10, §13 + SME | To triage |  |  |  | Not started
KA-OUT-024 | Choosing campaign-level mitigation | Decision Guide | 04 Outbound | 11 | 3 | D11: Identifying and actioning on campaigns D11: Hands on: Campaigns | 2 | M-W3-01, A-D15 | Guide §13 + SME | To triage |  |  |  | Not started
KA-PB-003 | Proactive hunting: questions and queries | Workflow / SOP | 06 Playbooks | 13 | 3 | D13: Shadow a proactive hunt | 1 | A-D15 | Guide §10 + SME | To triage |  |  |  | Not started
KA-GEN-008 | Escalation contacts | Reference | 00 Start Here | 14 | 3 | D14: Guardrails and escalation refresher | 1 | M-W3-03, A-D15 | SME / Ops | To triage |  |  |  | Not started

## LMS items
LMS modules and assessments
Planned questions are suggested starting points (4 per module or check, 20 for A-D06, 15 scenarios for A-D10, 30 for A-D15); adjust them in the yellow column.
LMS ID | Title | Type | Week | Day | Curriculum row(s) | Linked Quip articles | Trainer Guide | Planned questions | Status
M-W1-01 | Team Mission & Objectives - Mail OPS | Module | 1 | 1 | Team Mission & Objectives - Mail OPS | KA-FND-001 | None | 4 | Not started
M-W1-02 | Privacy principles and data handling boundaries | Module | 1 | 1 | Privacy principles and data handling boundaries | KA-FND-002 | None | 4 | Not started
M-W1-03 | iCloud and iCloud Mail | Module | 1 | 1 | iCloud and iCloud Mail | KA-FND-003 | None | 4 | Not started
M-W1-04 | iCloud+ mail features | Module | 1 | 1 | iCloud+ mail features | KA-FND-004 | None | 4 | Not started
M-W1-05 | Mail flow architecture | Module | 1 | 2 | Mail flow architecture | KA-FND-005 | TG-M-W1-05 | 4 | Not started
M-W1-06 | Tool Overview: Heimdall | Module | 1 | 2 | Tool Overview: Heimdall | KA-TOOL-002, KA-FND-006, KA-OUT-020, KA-OUT-021 | None | 4 | Not started
M-W1-07 | URL/SUPs | Check-only module | 1 | 2 | URL/SUPs | KA-IN-001 | TG-D02-url-sups | 4 | Not started
M-W1-08 | Tools overview - part 1 (Splunk) - Investigate | Module | 1 | 3 | Tools overview - part 1 (Splunk) - Investigate | KA-TOOL-003, KA-TOOL-004 | TG-M-W1-08 | 4 | Not started
M-W1-09 | Tools overview - part 1 (Sonar) - Investigate | Module | 1 | 3 | Tools overview - part 1 (Sonar) - Investigate | KA-TOOL-005, KA-GEN-006 | None | 4 | Not started
M-W1-10 | Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | Module | 1 | 3 | Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | KA-TOOL-006, KA-TOOL-007, KA-TOOL-008 | TG-M-W1-10 | 4 | Not started
M-W1-11 | Tools overview - part 3 (Radar, Slack, Quip) - Engineer | Module | 1 | 4 | Tools overview - part 3 (Radar, Slack, Quip) - Engineer | KA-TOOL-009, KA-TOOL-010 | None | 4 | Not started
M-W1-12 | Tools overview - part 4 (Khiron, iHawk) - Other tools | Module | 1 | 4 | Tools overview - part 4 (Khiron, iHawk) - Other tools | KA-TOOL-011, KA-TOOL-012 | None | 4 | Not started
M-W1-13 | The 14-stage milter chain | Module | 1 | 4 | The 14-stage milter chain | KA-FND-007 | TG-M-W1-13 | 4 | Not started
M-W1-14 | Inbound Mail Flow: Deep Dive | Module | 1 | 5 | Inbound Mail Flow: Deep Dive | KA-FND-009 | TG-M-W1-14 | 4 | Not started
M-W1-15 | Outbound Mail Flow: Deep Dive | Module | 1 | 5 | Outbound Mail Flow: Deep Dive | KA-FND-010 | TG-M-W1-15 | 4 | Not started
A-D06 | Week 1 Knowledge Check | Assessment | 2 | 6 | Week 1 Knowledge Check | KA-FND-001, KA-FND-002, KA-FND-003, KA-FND-004, KA-FND-005, KA-FND-006, KA-FND-007, KA-FND-008, KA-FND-009, KA-FND-010, KA-GEN-006, KA-IN-001, KA-IN-002, KA-OUT-001, KA-OUT-020, KA-OUT-021, KA-OUT-022, KA-TOOL-001, KA-TOOL-002, KA-TOOL-003, KA-TOOL-004, KA-TOOL-005, KA-TOOL-006, KA-TOOL-007, KA-TOOL-008, KA-TOOL-009, KA-TOOL-010, KA-TOOL-011, KA-TOOL-012 | TG-D06-knowledge-check | 20 | Not started
M-W2-01 | Our operating model: Identify, Mitigate, Engineer | Module | 2 | 6 | Our operating model: Identify, Mitigate, Engineer | KA-FND-011 | TG-M-W2-01 | 4 | Not started
M-W2-02 | Abuse landscape | Module | 2 | 6 | Abuse landscape | KA-FND-012 | None | 4 | Not started
M-W2-03 | Abuse landscape in iCloud Outbound | Check-only module | 2 | 6 | Abuse landscape in iCloud Outbound | KA-OUT-002, KA-OUT-003 | TG-D06-outbound-abuse | 4 | Not started
M-W2-04 | Types/Actions on accounts | Check-only module | 2 | 7 | Types/Actions on accounts | KA-OUT-010, KA-OUT-011 | TG-D07-account-actions | 4 | Not started
M-W2-05 | Actioning a case | Module | 2 | 7 | Actioning a case | KA-GEN-005, KA-GEN-006, KA-FND-013 | TG-M-W2-05 | 4 | Not started
M-W2-06 | Working with Postmaster | Module | 2 | 9 | Working with Postmaster | KA-PM-001, KA-PM-002, KA-PM-003, KA-PM-004 | TG-M-W2-06 | 4 | Not started
M-W2-07 | Other Ops workflow - Spike in user spam reports | Module | 2 | 9 | Other Ops workflow - Spike in user spam reports | KA-PB-001 | TG-M-W2-07 | 4 | Not started
M-W2-08 | Other Ops workflow - Outbound abuse | Module | 2 | 9 | Other Ops workflow - Outbound abuse | KA-PB-002 | TG-M-W2-08 | 4 | Not started
A-D10 | Week 2 Practical Assessment | Assessment | 2 | 10 | Week 2 Practical Assessment | KA-FND-011, KA-FND-012, KA-FND-013, KA-GEN-005, KA-GEN-006, KA-OUT-002, KA-OUT-003, KA-OUT-010, KA-OUT-011, KA-OUT-012, KA-PB-001, KA-PB-002, KA-PM-001, KA-PM-002, KA-PM-003, KA-PM-004 | TG-D10-assessment | 15 | Not started
M-W3-01 | Identifying and actioning on campaigns | Check-only module | 3 | 11 | Identifying and actioning on campaigns | KA-OUT-023, KA-OUT-024, KA-OUT-020, KA-OUT-021 | TG-D11-campaigns | 4 | Not started
M-W3-02 | Engineering hand-off: writing a Radar | Module | 3 | 11 | Engineering hand-off: writing a Radar | KA-GEN-007, KA-TOOL-009 | None | 4 | Not started
M-W3-03 | Guardrails and escalation refresher | Module | 3 | 14 | Guardrails and escalation refresher | KA-FND-013, KA-GEN-008 | None | 4 | Not started
A-D15 | Final Certification (theory and practical) | Assessment | 3 | 15 | Final Certification - Theory; Final Certification - Practical | KA-FND-001, KA-FND-002, KA-FND-003, KA-FND-004, KA-FND-005, KA-FND-006, KA-FND-007, KA-FND-008, KA-FND-009, KA-FND-010, KA-FND-011, KA-FND-012, KA-FND-013, KA-GEN-005, KA-GEN-006, KA-GEN-007, KA-GEN-008, KA-IN-001, KA-IN-002, KA-OUT-001, KA-OUT-002, KA-OUT-003, KA-OUT-010, KA-OUT-011, KA-OUT-012, KA-OUT-020, KA-OUT-021, KA-OUT-022, KA-OUT-023, KA-OUT-024, KA-PB-001, KA-PB-002, KA-PB-003, KA-PM-001, KA-PM-002, KA-PM-003, KA-PM-004, KA-TOOL-001, KA-TOOL-002, KA-TOOL-003, KA-TOOL-004, KA-TOOL-005, KA-TOOL-006, KA-TOOL-007, KA-TOOL-008, KA-TOOL-009, KA-TOOL-010, KA-TOOL-011, KA-TOOL-012 | TG-D15-certification | 30 | Not started
[7 empty] | Total questions | 169

## Training Kit
Training Kit items (restricted folder 90 Training Kit)
Trainer Guides and Hands-on Activities. Activities rely on SME sample data listed in the curriculum workbook's SME inputs sheet.
ID | Title | Type | First used (day) | Curriculum row(s) | Quip articles it points to | Owner | Status
TG-D01-icloud-handson | Trainer Guide: Hands on: iCloud and iCloud+ Mail | Trainer Guide | 1 | Hands on: iCloud and iCloud+ Mail | KA-FND-003, KA-FND-004 |  | Not started
TG-GEN-recap-wrap | Trainer Guide: Daily recap and wrap-up | Trainer Guide | 1 | Day n Recap Quick Wrap-Up | None |  | Not started
HA-FND-001 | iCloud and iCloud+ Mail hands-on | Hands-on Activity | 1 | Hands on: iCloud and iCloud+ Mail | KA-FND-003, KA-FND-004 |  | Not started
TG-D02-heimdall-walkthrough | Trainer Guide: Tool Walkthrough: Heimdall | Trainer Guide | 2 | Tool Walkthrough: Heimdall | KA-TOOL-002, KA-OUT-020, KA-OUT-022 |  | Not started
TG-D02-url-sups | Trainer Guide: URL/SUPs | Trainer Guide | 2 | URL/SUPs Hands on: URL/SUPs | KA-IN-001 |  | Not started
TG-M-W1-05 | Trainer Guide: Mail flow architecture | Trainer Guide | 2 | Mail flow architecture | KA-FND-005 |  | Not started
HA-IN-001 | URL/SUP practice requests | Hands-on Activity | 2 | Hands on: URL/SUPs | KA-IN-001 |  | Not started
HA-TOOL-002 | Write and read back a Heimdall rule | Hands-on Activity | 2 | Tool Walkthrough: Heimdall | KA-TOOL-002, KA-OUT-020, KA-OUT-022 |  | Not started
TG-D03-sonar-handson | Trainer Guide: Hands on: Sonar | Trainer Guide | 3 | Hands on: Sonar | KA-TOOL-005, KA-GEN-006 |  | Not started
TG-M-W1-08 | Trainer Guide: Tools overview - part 1 (Splunk) - Investigate | Trainer Guide | 3 | Tools overview - part 1 (Splunk) - Investigate Hands on: Splunk | KA-TOOL-003, KA-TOOL-004 |  | Not started
TG-M-W1-10 | Trainer Guide: Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | Trainer Guide | 3 | Tools overview - part 2 (Proofpoint, Bazooka, Gattler) - Mitigate | KA-TOOL-006, KA-TOOL-007, KA-TOOL-008 |  | Not started
HA-TOOL-001 | Splunk indexes and queries round robin | Hands-on Activity | 3 | Hands on: Splunk | KA-TOOL-004 |  | Not started
HA-TOOL-003 | Sonar: open, read and update a sample case | Hands-on Activity | 3 | Hands on: Sonar | KA-TOOL-005, KA-GEN-006 |  | Not started
TG-D04-header-analysis | Trainer Guide: Hands on: Header analysis with samples | Trainer Guide | 4 | Hands on: Header analysis with samples | KA-FND-008, KA-FND-007 |  | Not started
TG-D04-tools-by-stage | Trainer Guide: Hands on: Tools by stage | Trainer Guide | 4 | Hands on: Tools by stage | KA-TOOL-001 |  | Not started
TG-M-W1-13 | Trainer Guide: The 14-stage milter chain | Trainer Guide | 4 | The 14-stage milter chain | KA-FND-007 |  | Not started
HA-FND-002 | Header analysis with samples | Hands-on Activity | 4 | Hands on: Header analysis with samples | KA-FND-008, KA-FND-007 |  | Not started
HA-TOOL-004 | Match the tool to the task | Hands-on Activity | 4 | Hands on: Tools by stage | KA-TOOL-001 |  | Not started
TG-D05-inbound-tracing | Trainer Guide: Hands on: Inbound mail tracing | Trainer Guide | 5 | Hands on: Inbound mail tracing | KA-IN-002 |  | Not started
TG-D05-outbound-tracing | Trainer Guide: Hands on: Outbound mail tracing | Trainer Guide | 5 | Hands on: Outbound mail tracing | KA-OUT-001 |  | Not started
TG-M-W1-14 | Trainer Guide: Inbound Mail Flow: Deep Dive | Trainer Guide | 5 | Inbound Mail Flow: Deep Dive | KA-FND-009 |  | Not started
TG-M-W1-15 | Trainer Guide: Outbound Mail Flow: Deep Dive | Trainer Guide | 5 | Outbound Mail Flow: Deep Dive | KA-FND-010 |  | Not started
HA-IN-002 | Inbound mail tracing | Hands-on Activity | 5 | Hands on: Inbound mail tracing | KA-IN-002 |  | Not started
HA-OUT-001 | Outbound mail tracing | Hands-on Activity | 5 | Hands on: Outbound mail tracing | KA-OUT-001 |  | Not started
TG-D06-knowledge-check | Trainer Guide: Week 1 Knowledge Check | Trainer Guide | 6 | Week 1 Knowledge Check Knowledge Check Review | None |  | Not started
TG-D06-outbound-abuse | Trainer Guide: Abuse landscape in iCloud Outbound | Trainer Guide | 6 | Abuse landscape in iCloud Outbound | KA-OUT-002, KA-OUT-003 |  | Not started
TG-M-W2-01 | Trainer Guide: Our operating model: Identify, Mitigate, Engineer | Trainer Guide | 6 | Our operating model: Identify, Mitigate, Engineer | KA-FND-011 |  | Not started
TG-D07-account-actions | Trainer Guide: Types/Actions on accounts | Trainer Guide | 7 | Types/Actions on accounts | KA-OUT-010, KA-OUT-011 |  | Not started
TG-D07-sample-accounts | Trainer Guide: Hands-on with sample accounts | Trainer Guide | 7 | Hands-on with sample accounts | KA-OUT-010, KA-OUT-011, KA-OUT-012 |  | Not started
TG-M-W2-05 | Trainer Guide: Actioning a case | Trainer Guide | 7 | Actioning a case | KA-GEN-005, KA-GEN-006, KA-FND-013 |  | Not started
HA-OUT-002 | Sample accounts, guided (Day 7) | Hands-on Activity | 7 | Hands-on with sample accounts | KA-OUT-010, KA-OUT-011, KA-OUT-012 |  | Not started
TG-D08-case-review | Trainer Guide: Trainer case review | Trainer Guide | 8 | Trainer case review | None |  | Not started
TG-D08-sample-accounts | Trainer Guide: Hands-on with sample accounts | Trainer Guide | 8 | Hands-on with sample accounts | KA-OUT-010, KA-OUT-011, KA-OUT-012 |  | Not started
HA-OUT-003 | Sample accounts, independent (Day 8) | Hands-on Activity | 8 | Hands-on with sample accounts | KA-OUT-010, KA-OUT-011, KA-OUT-012 |  | Not started
TG-D09-postmaster-handson | Trainer Guide: Hands on: Postmaster cases | Trainer Guide | 9 | Hands on: Postmaster cases | KA-PM-002, KA-PM-003, KA-PM-004 |  | Not started
TG-M-W2-06 | Trainer Guide: Working with Postmaster | Trainer Guide | 9 | Working with Postmaster | KA-PM-001, KA-PM-002, KA-PM-003, KA-PM-004 |  | Not started
TG-M-W2-07 | Trainer Guide: Other Ops workflow - Spike in user spam reports | Trainer Guide | 9 | Other Ops workflow - Spike in user spam reports | KA-PB-001 |  | Not started
TG-M-W2-08 | Trainer Guide: Other Ops workflow - Outbound abuse | Trainer Guide | 9 | Other Ops workflow - Outbound abuse | KA-PB-002 |  | Not started
HA-PM-001 | Postmaster sample cases | Hands-on Activity | 9 | Hands on: Postmaster cases | KA-PM-002, KA-PM-003, KA-PM-004 |  | Not started
TG-D10-assessment | Trainer Guide: Week 2 Practical Assessment | Trainer Guide | 10 | Week 2 Practical Assessment Assessment Debrief | None |  | Not started
TG-D10-scenarios | Trainer Guide: Hands on: Postmaster and triage scenarios | Trainer Guide | 10 | Hands on: Postmaster and triage scenarios | KA-PM-002, KA-PB-001, KA-PB-002 |  | Not started
HA-PB-001 | Postmaster and triage scenarios | Hands-on Activity | 10 | Hands on: Postmaster and triage scenarios | KA-PM-002, KA-PB-001, KA-PB-002 |  | Not started
TG-D11-campaigns | Trainer Guide: Identifying and actioning on campaigns | Trainer Guide | 11 | Identifying and actioning on campaigns Hands on: Campaigns | KA-OUT-023, KA-OUT-024, KA-OUT-020, KA-OUT-021, KA-TOOL-004 |  | Not started
HA-OUT-004 | Campaign hunt in sample data | Hands-on Activity | 11 | Hands on: Campaigns | KA-OUT-023, KA-OUT-024, KA-TOOL-004 |  | Not started
TG-D12-case-review | Trainer Guide: Trainer case review | Trainer Guide | 12 | Trainer case review | None |  | Not started
TG-D12-outbound-handson | Trainer Guide: Outbound Hands-on | Trainer Guide | 12 | Outbound Hands-on | KA-OUT-003, KA-OUT-010, KA-OUT-011, KA-PB-002 |  | Not started
HA-OUT-005 | Outbound case set (Day 12) | Hands-on Activity | 12 | Outbound Hands-on | KA-OUT-003, KA-OUT-010, KA-OUT-011, KA-PB-002 |  | Not started
TG-D13-outbound-handson | Trainer Guide: Outbound Hands-on | Trainer Guide | 13 | Outbound Hands-on | KA-OUT-003, KA-OUT-010, KA-OUT-023 |  | Not started
TG-D13-rule-review | Trainer Guide: Proofpoint and Heimdall rule review | Trainer Guide | 13 | Proofpoint and Heimdall rule review | KA-TOOL-002, KA-TOOL-006, KA-OUT-021 |  | Not started
TG-D13-shadowing | Trainer Guide: Shadow a proactive hunt | Trainer Guide | 13 | Shadow a proactive hunt | KA-PB-003 |  | Not started
HA-OUT-006 | Outbound case set with campaign-linked accounts (Day 13) | Hands-on Activity | 13 | Outbound Hands-on | KA-OUT-003, KA-OUT-010, KA-OUT-023 |  | Not started
TG-D14-nesting | Trainer Guide: Nesting: supervised mixed queue | Trainer Guide | 14 | Nesting: supervised mixed queue QA feedback session | KA-GEN-005 |  | Not started
TG-D15-certification | Trainer Guide: Final Certification - Theory | Trainer Guide | 15 | Final Certification - Theory Final Certification - Practical | None |  | Not started
TG-D15-results | Trainer Guide: Results and development plans | Trainer Guide | 15 | Results and development plans Programme close and feedback | None |  | Not started
TG-D15-transition | Trainer Guide: Transition to process | Trainer Guide | 15 | Transition to process | KA-GEN-001 |  | Not started